## Internal_Risks
Project start | 2020-05-01 | IDEALFUEL - Internal risks
Today | 2021-04-23
Bio-HFO production | [20 empty] | 3
#N/A
ECAS ID | Risk |  |  | Impact 1 = Low 2 = Medium 3 = High | Probability 1 = Low 2 = Medium 3 = High | Effect | Risk Mitigation |  | Remaining Risk |  |  | State of play of the mitigation measures
| Identified Risk | Involved WPs | Effect | I | P | E | Approach | Action | I | P | E | Action by: | Status: | Ready: | Comments | In GA | Risk |  | Remaining risk
[17 empty] | I | P | I | P
1 | No suitable, large scale reactor available, or delayed, e.g. due to breakdown or other unforeseen factor | 2 | Project work delayed or reduced ability to deliver | 1 | 3 | 3 |  | Outsource to third-party biorefineries that have suitable equipment, e.g. Attis Innovations (USA) or Sekab (SE) | 1 | 2 | 2 | VER |  |  | No action needed yet |  | 2 | 4 | 2 | 3 | Low | Medium | High
2 | CLO processes do not scale up properly due to unforeseen factors | 2 | Reduced ability to deliver | 1 | 2 | 2 |  | In the project 2 routes will be tested, i.e. route#1 Vertoro androute#2 Bloom, if one of them does not scale properly the other process will act as a backup facility | 1 | 1 | 1 | VER / BLOOM |  |  | No action needed yet |  | 2 | 3 | 2 | 2
3 | Lack of fuel availability for WP4 and 5 | 2,3,4,5 | Project work delayed since project partners depend on these fuels and could not start their work | 2 | 3 | 6 |  | Surrogate fuels can be used, blending with HFO for the largescale engine testing to test the effect of only a few percent of Bio-HFO on the engine performance. | 1 | 1 | 1 | ALL |  |  | This carefully monitored and discussed within the consortium. No action needed yet. |  | 3 | 4 | 2 | 2
4 | Producing Bio-HFO is of insufficient quality as marine fuel. | 3,4,5 | Project work delayed since project partners depend on these fuels and could not start their work | 2 | 2 | 4 |  | Good quality of Bio-HFO is absolutely required. Numerous technical solutions are available to improve fuel quality, however might prove too costly. Combination of further conditioning and additivation may be considered if too much off-spec oil is produced. | 1 | 2 | 2 | GOOD |  |  | No action needed yet |  | 3 | 3 | 2 | 3
5 | Technical issues delay pilot-scale production of optimized HDO catalyst, with a potential effect on further project tasks. | 3,4,5 | Project work delayed since project partners depend on these fuels and could not start their work | 2 | 3 | 6 |  | Resort to commercially available catalysts, e.g. Co-MoOx/Al2O3 as fallback option. Even if not ad-hoc developed for optimal performance on CLO feeds, they would enable, after carbidization activation, the HDO process upscaling to be carried out, likely at the expenses of the yield to the final biofuel. | 2 | 2 | 4 | CSIC/VER |  |  | Commercial catalysts are being tested as a reference case. This screening will give directions of a potential commercial catalysts that can be used on short notice. Further implementation of the mitigation activities will be done when needed. |  | 3 | 4 | 3 | 3
6 | Final upgraded Bio-HFO fuel not fully meeting the specs listed as a target (see WP2 description). | 3,4,5 |  | 2 | 2 | 4 |  | Fuel formulation and blending recipes with conventional HFO can be adapted to avoid propagation of this risk to WP5. | 1 | 2 | 2 | OWI/GOOD |  |  | No action needed yet |  | 3 | 3 | 2 | 3
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
Engine tasks
ECAS ID | Risk |  |  | Impact 1 = Low 2 = Medium 3 = High | Probability 1 = Low 2 = Medium 3 = High | Effect | Risk Mitigation |  | Remaining Risk |  |  | State of play of the mitigation measures
| Identified Risk | Involved WPs | Effect | I | P | E | Approach | Action | I | P | E | Action by: | Status: | Ready: | Comments | In GA | Risk |  | Remaining risk
[17 empty] | I | P | I | P
7 | Unexpected high emissions, in particular NOx, HC during transient conditions | 5 |  | 2 | 2 | 4 |  | More efforts needs to be implemented to analyse the fuel and ignition timing of this fuel. The consortium has key research facilities available to assess this in more detail if required | 1 | 1 | 1 | TUE/WINGD |  |  | No action needed yet |  | 3 | 3 | 2 | 2
8 | Single cylinder buildup delays | 5 |  | 1 | 2 | 2 |  | The results of the 2-stroke engine will become available later but this has virtually no impact on other partners. Other (external) facilities are available to do this testing if needed. | 1 | 1 | 1 | WINGD |  |  | No action needed yet |  | 2 | 3 | 2 | 2
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
Lignin oil characterisation
ECAS ID | Risk |  |  | Impact 1 = Low 2 = Medium 3 = High | Probability 1 = Low 2 = Medium 3 = High | Effect | Risk Mitigation |  | Remaining Risk |  |  | State of play of the mitigation measures
| Identified Risk | Involved WPs | Effect | I | P | E | Approach | Action | I | P | E | Action by: | Status: | Ready: | Comments | In GA | Risk |  | Remaining risk
[17 empty] | I | P | I | P
| Fuel properties measurements at different locations/partners are not consistent | 2,3,4 | Diffulties to define the route for next steps (e.g. catalysts development). More measurements are needed, that could delay the progress of the project | 1 | 2 | 2 |  | The consortium is setting up an measurement protocol for the key fuel properties.This protocal will support the consistency of the measurements between partners. | 1 | 1 | 1 | Vertoro |  | no | Protocol is being setup at the moment, and will be updated regularly |  | 2 | 3 | 2 | 2
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
Management
ECAS ID | Risk |  |  | Impact 1 = Low 2 = Medium 3 = High | Probability 1 = Low 2 = Medium 3 = High | Effect | Risk Mitigation |  | Remaining Risk |  |  | State of play of the mitigation measures
| Identified Risk | Involved WPs | Effect | I | P | E | Approach | Action | I | P | E | Action by: | Status: | Ready: |  | In GA | Risk |  | Remaining risk
[17 empty] | I | P | I | P
9 | Loss of key staff in the IDEALFUEL project | ALL | Project work delayed or reduced ability to deliver | 3 | 1 | 3 |  | The consortium will implement diversity in its key staff to cover loss of staff. This is furthermore achieved by regular meetings of the coordinating team and the WPLB telephone conferences. Due to this open communication it is ensured that the consortium will receive the relevant information on all levels. | 2 | 1 | 2 | TU/e |  | yes | Implemented but not needed |  | 4 | 2 | 3 | 2
| Change of project coordinator | ALL | Communication disruptive, delays in implementation of work | 1 | 1 | 1 |  | This is being achieved by regular meetings of the coordinating team and the WPL board telephone conferences. Due to this open communication it is ensured that the consortium will receive the relevant information on all levels. | 1 | 1 | 1 | TU/e |  |  |  |  | 2 | 2 | 2 | 2
| Underperforming partner | ALL | Project work delayed or reduced ability to deliver | 2 | 2 | 4 |  | Several instruments will be implemented by the consortium to lower the risk of a underperforming partner. Among these instruments are the regular telephone conferences of the WPL board, process of quality check of the deliverables and milestones and a regular discussion with respect to risk monitoring. | 1 | 1 | 1 | TU/e |  | yes | Several instruments have been implemented by the consortium to lower the risk of a underperforming partner. Among these instruments are the regular telephone conferences of the WPL board, process of quality check of the deliverables and milestones and a regular discussion with respect to risk monitoring. |  | 3 | 3 | 2 | 2
| Defaulting partner | ALL | Project work delayed or reduced ability to deliver | 3 | 1 | 3 |  | Several instruments have been implemented by the consortium to lower the risk of a defaulting partner. Among these instruments are the regular telephone conferences of the WPL board, process of quality check of the deliverables and milestones and a regular discussion with respect to risk monitoring. | 2 | 1 | 2 | TU/e |  | yes | Several instruments have been implemented by the consortium to lower the risk of a defaulting partner. Among these instruments are the regular telephone conferences of the WPL board, process of quality check of the deliverables and milestones and a regular discussion with respect to risk monitoring. |  | 4 | 2 | 3 | 2
| Partner withdrawal | ALL | Project work delayed or reduced ability to deliver | 3 | 1 | 3 |  | The coordinating team has established an open-minded and trustful communication flow with the consortium partners by being pro-actively, very responsive and descriptive when clarifying any questions. The coordinating team has internalized and exemplified an exemplary function for communication and commitment to the project and the partners. This has contributed to a high level interactive and open-minded interplay among the partners to principally follow a clear joint collaboration to successfully implement the project. Initially planned for WP Leaders only, the coordinating team has also invited the other partners to these e-conferences to show that all need to know the status and the issues for discussion and clarification in all work packages at any time. Communication has taken place regularly and very often by email and phone, bilaterally and with specific groups to ensure a stable exchange of all project-relevant progresses and issues and towards potential connections outside the project world. Consortium partners are therefore on the same track be able to take over responsibilities and specific tasks. | 2 | 1 | 2 | TU/e |  | yes | The coordinating team has established an open-minded and trustful communication flow with the consortium partners by being pro-actively, very responsive and descriptive when clarifying any questions. The coordinating team has internalized and exemplified an exemplary function for communication and commitment to the project and the partners. This has contributed to a high level interactive and open-minded interplay among the partners to principally follow a clear joint collaboration to successfully implement the project. Initially planned for WP Leaders only, the coordinating team has also invited the other partners to these e-conferences to show that all need to know the status and the issues for discussion and clarification in all work packages at any time. Communication has taken place regularly and very often by email and phone, bilaterally and with specific groups to ensure a stable exchange of all project-relevant progresses and issues and towards potential connections outside the project world. Consortium partners are therefore on the same track be able to take over responsibilities and specific tasks. |  | 4 | 2 | 3 | 2
| Impact COVID19 | ALL | Project work delayed or reduced ability to deliver | 2 | 2 | 4 | [10 empty] | 3 | 3 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1

## External_Risks
1
| Project start | 2020-05-01 | IDEALFUEL - External risks
| Today | 2021-04-23
Legislation and Normative Issues
| ECAS ID | Risk |  |  | Impact 1 = Low 2 = Medium 3 = High | Probability 1 = Low 2 = Medium 3 = High | Effect | Risk Mitigation |  | Remaining Risk |  |  | State of play of the mitigation measures
|  | Identified Risk | Involved WPs | Effect | I | P | E | Approach | Action | I | P | E | Action by: | Status: | Ready: | Comments | Mentioned In GA | Risk |  | Remaining risk
[18 empty] | I | P | I | P
|  | Bio-HFO not recognized as "standard" fuel |  |  | 3 | 3 | 9 |  |  | 2 | 2 | 4 | [5 empty] | 4 | 4 | 3 | 3
| 10 | Current legislation not adapted for use of Bio-HFO, resulting in uncertainty on emission limits, permit requirments etc. |  |  | 2 | 2 | 4 |  | Get an overview of all legal issues and start communication actions with relevant stakeholders to overcome them. One key stakeholder IMO is in our sounding board. | 1 | 1 | 1 | [5 empty] | 3 | 3 | 2 | 2
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
Market uptake
| ECAS ID | Risk |  |  | Impact 1 = Low 2 = Medium 3 = High | Probability 1 = Low 2 = Medium 3 = High | Effect | Risk Mitigation |  | Remaining Risk |  |  | State of play of the mitigation measures
|  | Identified Risk | Involved WPs | Effect | I | P | E | Approach | Action | I | P | E | Action by: | Status: | Ready: | Comments | In GA
Health safety and envrionment
:)
| ECAS ID | Risk |  |  | Impact 1 = Low 2 = Medium 3 = High | Probability 1 = Low 2 = Medium 3 = High | Effect | Risk Mitigation |  | Remaining Risk |  |  | State of play of the mitigation measures
|  | Identified Risk | Involved WPs | Effect | I | P | E | Approach | Action | I | P | E | Action by: | Status: | Ready: | Comments | Mentioned In GA | Risk |  | Remaining risk
[18 empty] | I | P | I | P
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
Economy
| ECAS ID | Risk |  |  | Impact 1 = Low 2 = Medium 3 = High | Probability 1 = Low 2 = Medium 3 = High | Effect | Risk Mitigation |  | Remaining Risk |  |  | State of play of the mitigation measures
|  | Identified Risk | Involved WPs | Effect | I | P | E | Approach | Action | I | P | E | Action by: | Status: | Ready: | Comments | In GA | Risk |  | Remaining risk
[18 empty] | I | P | I | P
|  | Bio-HFO more expensive than competing fuel |  | High price will hamper market introduction | 3 | 3 | 9 |  |  | 2 | 3 | 6 | [5 empty] | 4 | 4 | 3 | 4
|  | Logistics of Bio-HFO not in place |  | Chicken-egg discussion hampering market introduction. | 2 | 2 | 4 |  |  | 1 | 2 | 2 | [5 empty] | 3 | 3 | 2 | 3
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
Storage and Transport
| ECAS ID | Risk |  |  | Impact 1 = Low 2 = Medium 3 = High | Probability 1 = Low 2 = Medium 3 = High | Effect | Risk Mitigation |  | Remaining Risk |  |  | State of play of the mitigation measures
|  | Identified Risk | Involved WPs | Effect | I | P | E | Approach | Action | I | P | E | Action by: | Status: | Ready: | Comments | In GA | Risk |  | Remaining risk
[18 empty] | I | P | I | P
|  | Standard storage systems not suitable for Bio-HFO |  | Storage system will not function, leakages | 3 | 3 | 9 |  |  | 2 | 2 | 4 | [5 empty] | 4 | 4 | 3 | 3
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 | 1 | 1
Note on F19: 1 = LOW 2 = MEDIUM 3 = HIGH
Note on G19: 1 = LOW 2 = MEDIUM 3 = HIGH

## Risk Log
Risk Log
Risk Rank | Risk Nr. | Effect | Risk Nr. |  | Effect
|  |  | 3 | Lack of fuel availability for WP4 and 5 | 6
|  |  | 5 | Technical issues delay pilot-scale production of optimized HDO catalyst, with a potential effect on further project tasks. | 6
|  |  | 4 | Producing Bio-HFO is of insufficient quality as marine fuel. | 4
|  |  | 6 | Final upgraded Bio-HFO fuel not fully meeting the specs listed as a target (see WP2 description). | 4
|  |  | 7 | Unexpected high emissions, in particular NOx, HC during transient conditions | 4
|  |  | 0 | Underperforming partner | 4
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | Engine tasks | 0 | 0
|  |  | 0 | 0 | 0
|  |  | ECAS ID | Risk | Effect
|  |  | 0 | Identified Risk | E
|  |  | 0 | 0 | 0
|  |  | 0 | Impact COVID19 | 4
|  |  | 1 | No suitable, large scale reactor available, or delayed, e.g. due to breakdown or other unforeseen factor | 3
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | Lignin oil characterisation | 0 | 0
|  |  | 0 | 0 | 0
|  |  | ECAS ID | Risk | Effect
|  |  | 0 | Identified Risk | E
|  |  | 0 | 0 | 0
|  |  | 9 | Loss of key staff in the IDEALFUEL project | 3
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | Management | 0 | 0
|  |  | 0 | 0 | 0
|  |  | ECAS ID | Risk | Effect
|  |  | 0 | Identified Risk | E
|  |  | 0 | 0 | 0
|  |  | 0 | Defaulting partner | 3
|  |  | 0 | Partner withdrawal | 3
|  |  | 2 | CLO processes do not scale up properly due to unforeseen factors | 2
|  |  | 8 | Single cylinder buildup delays | 2
|  |  | 0 | Fuel properties measurements at different locations/partners are not consistent | 2
|  |  | 0 | Change of project coordinator | 1
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0

## Risk_matrix
Selection | Approach | Level | Status | Partners
yes | Avoid | Low | Open | TUE
no | Mitigate | Medium | Implemented | VER
| Accept | High | Executed | T4F
| Transfer |  |  | BLOOM
UNR
WINGD
GOOD
TKMS
OWI
CSIC
VARO
Matrix
H
M
L
| L | M | H
PROBABILITY
IMPACT